Report on the outcomes of a Virtual Mobility

Action number: CA23113

Grantee name: Baiba Martinsone

Virtual Mobility Details Title: Development of methodology for qualitative analysis of interview data Start and end date: 13/10/2025 to 28/10/2025

Description of the work carried out during the VM All planned activities have been completed. To initiate the qualitative analysis of interviews for the research “Understanding Eco-Anxiety and Eco-Depression Related to Climate Change: Perspectives from the General Public, Climate Activists, and Professionals”, interviews with respondents from three groups were carried out and transcribed. Based on this data, the methodology for qualitative analysis will be developed. This research and the following scientific publication are deliverables of the action’s working group.

Description of the VM main achievements and planned follow-up activities

The following tasks of the VMG have been completed and exceeded: 1) Conducted interviews with four policymakers, three people from the general society, and two environmental activists; 2) All interviews are anonymized, transcribed, and translated into English; 3) A draft thematic analysis template for one interview has been developed and translated into English. The outcomes create a basis for the data set and foster the research coordination "To identify individual sociodemographic characteristics and health factors that influence climate change-related mental health," and deliverable "D1.2: Scientific paper on qualitative experiences of eco-anxiety (M18)." The future follow-up collaboration with leaders of the working group and involved participants will include developing the whole data set, proceeding with data analysis, and preparing the scientific publication.

This report is submitted by the grantee to the Action MC for approval and for claiming payment of the awarded grant. The Grant Awarding Coordinator coordinates the evaluation of this report on behalf of the Action MC and instructs the GH for payment of the Grant.